## Sheet1
Index | Task | Days | Dependency | Comments | Status | Drop plan | Resource
1 | Designing UI and its approval |  |  | Designing of UI layout, data normalization and making a understanding clean on what to expect from the system. Make sure user requirement is matching the Ui
Physician Home health plan
Internal Medicine
Billing
2 | Input validation and processing of data |  |  | Writing Code for the UI and going throught various error validation and value checks.
Physician home health plan
internal medicine
Billing
3 | Database entries |  |  | Writing code to interact with the database and perform various other function related to database interaction.
Physican home health plan
internal medicine
billing
4 | Output functionality |  |  | Writing program module to create output parameters for the functionality and test modules with FAXing and Printing
FAX module
Print module
5 | Reports |  |  | Generation of various report that user might ask for. This needs to be clearly defined in the software specification
Designing and approval
Report generation
6 | Testing and Integration |  |  | Unit Testing, with module testing and end to end system testing
7 | Acceptance Testing |  |  | Beta level code to have user go through system test and provide its feedback. It might involve various bug fixing and other interaction as actual system is being tested
8 | Final Release |  |  | Final release code deployed on user site. With support to its various issues. We may need to provide various logging features if required.